## Open
SPAM
ERROR NUMBER | TEAM | TIME | REQUEST | PROBLEM | PROPOSED SOLUTION
TIMING ERRORS
SP_Timing_Errors_1 | RADAR | 2015-271T22:24:12 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_2 | RADAR | 2015-271T22:24:32 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_3 | RADAR | 2015-271T22:27:21 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_4 | RADAR | 2015-271T22:29:59 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_5 | SP | 2015-299T15:45:00 | SP_224EA_G34HEFNON299_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | SP to shorten downlink block in SASF
AP DOWNLINK CHECKS
ap_downlink1 | SP |  | SP_224EA_G34HEFNON299_PRIME | Error: SP_224EA_G34HEFNON299_PRIME start time does not match end of preceding observation period | SP to extend observation period
SPASS//SASF COMPARE
CIMS_SPASS_SASF_0780 | ISS | 2015-287T16:55:00 | ISS_223EN_PLUJTL001_PIE | SASF is not picking up at the previous custom attitude: Z Offset 174.49 (SASF) <> -174.49 (-10.0 deg) (Custom). | ISS needs to insert a negative sign in sasf offset
CIMS_SPASS_SASF_0781 | ISS | 2015-287T16:55:00 | ISS_223EN_PLUJTL001_PIE | SASF does not match the SPASS. Z Offset 3.739 (SASF) <> 0.0 (0.0 deg) (SPASS). | ISS to confirm this is okay
RESOURCE CHECKER
CIMS_RESOURCE_CHECK_732 | CIRS | 2015-299T16:45:00 | CIRS_224IC_DSCAL15299_SP | CIRS DSCAL occurs within the first 45 minutes of a Downlink Pass | Courtesy notification to CIRS--early changes during SIP for DSN, CIRS may wish to update timing.
CIMS_RESOURCE_CHECK_733 | CIRS | 2015-310T15:59:00 | CIRS_225IC_DSCAL15310_SP | CIRS DSCAL occurs within the first 45 minutes of a Downlink Pass | Courtesy notification to CIRS--early changes during SIP for DSN, CIRS may wish to update timing.
SPLAT
S91000005 | ISS | 2015-287T07:00:00 | ISS_223EN_ENCEL001_PIE | This observation has 180 degrees target motion, and possible SRU violations at closest approach (depending on secondary chosen). | Please include a 20 minute quiescent period due to the target motion, and either design with no SRU violations or include proper quiescent periods for that as well. The designer should provide the quiescent period time to the SIP lead in time for the science forum so AACS can use in in their RBOT analysis.
S91000199 | ISS | 2015-273T07:50:00 | ISS_222DI_DIONE002_PIE | This and the observations immediately before and after have total target (Dione) motion of 122 degrees over 3h30m. | Any observation >3 hours in which the target body travels > 60 degrees must include 20 minute quiescent periods every 3 hours. The last 20 minutes of this observation is at an inertial attitude to satisfy this guideline.
S91000204 | CIRS | 2015-328T04:15:00 | CIRS_226SA_LIMBINT001_PIE | The target of this observation -- Saturn -- covers 80 degrees of sky during the course of this six-hour observation. The requirement is <60 degrees of motion in a 3 hour observation. | The observation must include an inertially fixed quiescent period of 20 minutes. The designer should provide the quiescent period time to the SIP lead in time for the science forum so AACS can use in in their RBOT analysis.
S91000205 | CIRS | 2015-327T20:00:00 | CIRS_226TE_TETHYS001_PIE | The target of this observation -- Tethys -- covers 150 degrees of sky during the course of this three-hour, thirty-minute observation. | The observation must include an inertially fixed quiescent period of 20 minutes. The designer should provide the quiescent period time to the SIP lead in time for the science forum so AACS can use in in their RBOT analysis.
S91000206 | MP SP | 2015-267T23:48:12 | Delay Canberra HEF maintenance | According to CIMS, the Canberra Complex is down from 267T20:32 - 268T02:32. The Canberra HEF is requested from 267T23:48 - 08:48. This is an OTM Prime Pass. | Request delay of Canberra HEF maintenance until after OTP pass is complete.
S91000207 | CDS ENGR SP | 2015-273T02:02:00 | ENGR_222NA_DUALPB271_CDS | This is a non-standard dual playback, with carryover on SSRs prior to high-value observation period as well as prior to the dual playback pass. During DSN negotiations, ensure that SSR-A is emptied before the pointers are reset. This item cannot be closed until the DSN negotiations are complete for both downlink passes, or the dual playback is deleted. | Resolve during DSN negotiations.
S91000208 | MP SP | 2015-280T23:01:00 | Delay Canberra BWG Maintenance | According to CIMS, the Canberra Complex is down from 280T19:31 - 281T01:31. The Canberra BWG station is requested from 280T23:01 - 08:01. | Request delay of Canberra BWG maintenance until downlink is complete.
S91000209 | CIRS INMS RADAR SP | 2015-271T20:37:12 | INMS_222TI_TITAN113001_PRIME | T113: INMS inbound and RADAR C/A observations both have CIRS heating. At PSG for T113 CAPS reallocation, CIRS has agreed to accept a heating consumable up to 14.4K above T0. | Ensure the INMS and RADAR T113 observations together do not heat CIRS beyond 14.4K above T0, or CIRS to accept a new heating consumable value.
S91000297 | CIRS INMS SP VIMS | 2015-301T13:30:00 | INMS_224EN_ENCEL21001_PIE | INMS_224EN_ENCEL21001_PIE has ~ 12.9 K of CIRS heating, and also a high amount of VIMS heating. | Get preliminary approval from CIRS and VIMS, write and approve waiver during SIP process.

## All
Input Files
z0900b_for_S91.cf
SCLKSCET.00162
140114AP_LT_13290_17265.TXT
CAS_14091_17263A.VP
140114BP_OP_13290_17265.TXT
S91_SIP_PORT1_GEOEPOCHS_150428.sasf
S91_SIP_PORT1_RIDEREPOCHS_150520.sasf
SP_S91_SIP_PORT2_DATAPOL_150527.sasf
SP_S91_SIP_PORT1_PDT_UG_150521.sasf
ULO_S91_SIP_PORT2_ATT_150601.sasf
ULO_S91_SIP_PORT2_SFOS_150601.sasf
CDA_S91_SIP_PORT1_150514.sasf
CIRS_S91_SIP_PORT2_150601.sasf
INMS_S91_SIP_PORT2_150601.sasf
ISS_S91_SIP_PORT2_150601.sasf
MAG_S91_SIP_PORT2_150529.sasf
MIMI_S91_SIP_PORT2_150601.sasf
NAV_S91_SIP_PORT1_UG1_150521.sasf
RADAR_S91_SIP_PORT2_150601.sasf
RPWS_S91_SIP_PORT2_150601.sasf
RSS_S91_SIP_PORT1_150514.sasf
UVIS_S91_SIP_PORT2_150601.sasf
VIMS_S91_SIP_PORT2_150530.sasf
SI_S91_SIP_PORT2_150528.sasf
vimsiops_S91_SIP_PORT1_150514.sasf
THERM_S91_PORT2.sasf
AACS_S91_SIP_PORT2_150527.sasf
CDS_S91_SIP_PORT2_150522.sasf
OPMODE_S91_SIP_PORT2_150528.sasf
This Merge Has No Files From
CAPS
ISSIOPS
IVD Files
RADAR_S91_SIP_T113_150514_Rm6.ivd
RADAR_S91_SIP_T113_150514_R.ivd
SPAM
ERROR NUMBER | TEAM | TIME | REQUEST | PROBLEM | PROPOSED SOLUTION
TIMING ERRORS
SP_Timing_Errors_1 | RADAR | 2015-271T22:24:12 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_2 | RADAR | 2015-271T22:24:32 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_3 | RADAR | 2015-271T22:27:21 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_4 | RADAR | 2015-271T22:29:59 | RADAR_222TI_T113OHSAR001_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | RADAR to fix, mismatch between 7OFFSET in PEF and SASF. Commands are backing into the time before their observation
SP_Timing_Errors_5 | SP | 2015-299T15:45:00 | SP_224EA_G34HEFNON299_PRIME | A 7OFFSET falls in a GAP between two SPASS intervals. | SP to shorten downlink block in SASF
SP_Timing_Errors_6 |  | 2015-316T06:53:59 | CIRS_225TI_MIDIRTMAP001_PRIME | Out of place: A(n) CIRS 7OFFSET command is exactly at the end of a deadtime window. | Per agreement with SCO and ULO, it is OK to have a 7OFFSET exactly at the end time of these gaps.
EARTH POINT ERRORS
(none)
VELOCITY AND ACCELERATION ERRORS
(none)
COMMANDS EXPANDED OUTSIDE OF SEQUENCE
(none)
TARGET OPTION LABEL ERRORS
(none)
PRECISION ERRORS
(none)
Duplicate Epochs
LMB Warnings
SP_LMBcheck_0 |  | - | - | The SASF contains no LMBs. If none expected disregard.
SEQGEN Violations Summary
sameSecondCommandConflict-0 |  | 2015-264T02:49:10 | SP-SMT_222NA_OBSERV264_NA_SPSPR, SP-SMT_LOAD_TAB_01 | 6CHG_CRC_NP, 6MOD_POL_TBL | Both Commands from SMT request.
sameSecondCommandConflict-1 |  | 2015-264T02:49:13 | SP-SMT_LOAD_TAB_01, SP-SMT_222NA_OBSERV264_NA_SPSPR | 6MOD_POL_TBL, 6SSR_CONFIG | Both Commands from SMT request.
sameSecondCommandConflict-2 |  | 2015-264T02:49:14 | SP-SMT_LOAD_TAB_01, SP-SMT_222NA_OBSERV264_NA_SPSPR | 6MOD_POL_TBL, 6SSR_CONFIG | Both Commands from SMT request.
sameSecondCommandConflict-3 |  | 2015-264T02:49:15 | SP-SMT_222NA_OBSERV264_NA_SPSPR, SP-SMT_LOAD_TAB_01 | 6CHG_CRC_NP, 6MOD_POL_TBL | Both Commands from SMT request.
sameSecondCommandConflict-4 |  | 2015-264T02:49:18 | SP-SMT_LOAD_TAB_01, SP-SMT_222NA_OBSERV264_NA_SPSPR | 6MOD_POL_TBL, 6SSR_CONFIG | Both Commands from SMT request.
sameSecondCommandConflict-5 |  | 2015-264T02:49:19 | SP-SMT_LOAD_TAB_01, SP-SMT_222NA_OBSERV264_NA_SPSPR | 6MOD_POL_TBL, 6SSR_CONFIG | Both Commands from SMT request.
sameSecondCommandConflict-6 |  | 2015-264T02:49:20 | SP-SMT_222NA_OBSERV264_NA_SPSPR, SP-SMT_LOAD_TAB_01 | 6CHG_CRC_NP, 6MOD_POL_TBL | Both Commands from SMT request.
sameSecondCommandConflict-47 |  | 2015-270T12:58:00 | SP-SMT_222NA_OBSERV270_NA, ENGR_222SC_RADWU270_PPS | 6CHG_SC_TM_IMM, 6SFP_MON_CNTL_NP | Allowed per SCO email 9/30/09. See spamNotes.
sameSecondCommandConflict-60 |  | 2015-271T12:37:12 | SP-SMT_222NA_OBSERV271_NA, ENGR_222SC_RADWU271_PPS | 6CHG_SC_TM_IMM, 6SFP_MON_CNTL_NP | Allowed per SCO email 9/30/09. See spamNotes.
sameSecondCommandConflict-173 |  | 2015-310T06:14:04 | SP-SMT_LOAD_TAB_02, SP-SMT_225NA_OBSERV310_NA | 6MOD_POL_TBL, 6POL_SCI_CNTL | Both Commands from SMT request.
sameSecondCommandConflict-191 |  | 2015-318T13:30:00 | SP-SMT_225NA_OBSERV318_NA, ENGR_225SC_RADWU318_PPS | 6CHG_SC_TM_IMM, 6SFP_MON_CNTL_NP | Allowed per SCO email 9/30/09. See spamNotes.
SEQGEN-0 |  | 2015-270T12:58:01.000 | ENGR_222SC_RADWU270_PPS | WARNING: X_TWTA-A is currently powered OFF.
SEQGEN-1 |  | 2015-270T20:12:56.000 | ENGR_222SC_DFPW270_PPS | WARNING: X_TWTA-A is currently powered OFF.
SEQGEN-2 |  | 2015-271T12:37:13.000 | ENGR_222SC_RADWU271_PPS | WARNING: X_TWTA-A is currently powered OFF.
SEQGEN-3 |  | 2015-271T23:14:08.000 | ENGR_222SC_DFPW271_PPS | WARNING: X_TWTA-A is currently powered OFF.
SEQGEN-4 |  | 2015-318T13:30:01.000 | ENGR_225SC_RADWU318_PPS | WARNING: X_TWTA-A is currently powered OFF.
SEQGEN-5 |  | 2015-318T18:29:56.000 | ENGR_225SC_DFPW318_PPS | WARNING: X_TWTA-A is currently powered OFF.
SMT ERRORS
SP_SMT_1 |  | 2015-270T12:58:00.000 | RADAR_222OT_WU4RADCAL132_RIDER | Found an activity whose data are NOT recorded in this telemetry mode S_N_ER_3 commanded at 2015-270T13:13:00.000. Volume of 8.667648 Mb not given data policing space. | OK--RADAR confirmed loss
SP_SMT_2 |  | 2015-271T12:37:12.000 | RADAR_222TI_T113WRMUP001_RIDER | Found an activity whose data are NOT recorded in this telemetry mode S_N_ER_3 commanded at 2015-271T12:52:12.000. Volume of 13.2313 Mb not given data policing space. | OK--RADAR confirmed loss
AP DOWNLINK CHECKS
ap_downlink1 | SP |  | SP_224EA_G34HEFNON299_PRIME | Error: SP_224EA_G34HEFNON299_PRIME start time does not match end of preceding observation period | SP to extend observation period
ap_downlink2 |  |  | SP_224EA_C70METOTP301_PRIME | Warning: SP_224EA_C70METOTP301_PRIME has an unusual gap time; usual for OTMs is 01:22:00 | OK--playback gap is in second half of split pass
ap_downlink3 |  |  | SP_226EA_G70METSEQ324_PRIME | Warning: SP_226EA_G70METSEQ324_PRIME is a SEQ upload pass and should be at least 9 hours in duration | OK--8hr45min dur is acceptable
SPASS//SASF COMPARE
CIMS_SPASS_SASF_0760 |  | 2015-264T02:54:00 | ENGR_222SC_KPTYBIAS464_PRIME | The CIMS request does not correspond to a request in the SASF | ignore, will go away in port3
CIMS_SPASS_SASF_0764 |  | 2015-271T19:37:12 | VIMS_222TI_REGMAP001_PRIME | SASF does not match the SPASS. Z Offset 5.0 (SASF) <> 0.0 (0.0 deg) (SPASS). | VIMs verified ok-start of mosaic
CIMS_SPASS_SASF_0780 | ISS | 2015-287T16:55:00 | ISS_223EN_PLUJTL001_PIE | SASF is not picking up at the previous custom attitude: Z Offset 174.49 (SASF) <> -174.49 (-10.0 deg) (Custom). | ISS needs to insert a negative sign in sasf offset
CIMS_SPASS_SASF_0781 | ISS | 2015-287T16:55:00 | ISS_223EN_PLUJTL001_PIE | SASF does not match the SPASS. Z Offset 3.739 (SASF) <> 0.0 (0.0 deg) (SPASS). | ISS to confirm this is okay
CIMS_SPASS_SASF_0798 |  | 2015-327T05:44:00 | VIMS_226SA_NHEMMAP001_PRIME | SASF does not match the SPASS: Z Offset -50.0 (SASF) <> 0.0 (0.0 deg) (SPASS). Offset tolerance applied was 2.0. | VIMs verified ok-start of mosaic
RESOURCE CHECKER
CIMS_RESOURCE_CHECK_732 | CIRS | 2015-299T16:45:00 | CIRS_224IC_DSCAL15299_SP | CIRS DSCAL occurs within the first 45 minutes of a Downlink Pass | Courtesy notification to CIRS--early changes during SIP for DSN, CIRS may wish to update timing.
CIMS_RESOURCE_CHECK_733 | CIRS | 2015-310T15:59:00 | CIRS_225IC_DSCAL15310_SP | CIRS DSCAL occurs within the first 45 minutes of a Downlink Pass | Courtesy notification to CIRS--early changes during SIP for DSN, CIRS may wish to update timing.
CIMS_RESOURCE_CHECK_748 |  | 2015-299T14:15:00 | SP_224EA_YGAP299_PRIME | Gap in Prime SPASS requests between SP_224EA_YGAP299_PRIME and SP_224EA_G34HEFNON299_PRIME. Gap of 000T00:45:00 is greater than or equal to 60 seconds. | OK, from change in downtime
CIMS_RESOURCE_CHECK_756 |  | 2015-303T21:30:00 | SP_224EA_C34HEFNON303_PRIME | ENGR Bias is detected during a Rolling downlink | SP_224EA_C34HEFNON303_PRIME: YGAP window short by 13 minutes, so KPTY bias rider overlaps downlink by 13 minutes. OK’d by SCO. Downlink will be shortened to accommodate Ybias if needed. Reevaluate in port3
CIMS_RESOURCE_CHECK_758 |  | 2015-301T14:52:43 | CIRS_224EN_ENCEL21001_INMS | Rider request CIRS_224EN_ENCEL21001_INMS start/end 2015-301T14:52:43/2015-301T15:52:43 <> Prime request INMS_224EN_ENCEL21001_PIE start/end 2015-301T13:30:00/2015-301T17:30:00 | Rider is shorter on purpose for data volume
CIMS_RESOURCE_CHECK_757 |  | 2015-301T14:52:43 | ISS_224EN_ENCEL21001_INMS | Rider request ISS_224EN_ENCEL21001_INMS start/end 2015-301T14:52:43/2015-301T15:52:43 <> Prime request INMS_224EN_ENCEL21001_PIE start/end 2015-301T13:30:00/2015-301T17:30:00 | Rider is shorter on purpose for data volume
SPLAT
S91000005 | ISS | 2015-287T07:00:00 | ISS_223EN_ENCEL001_PIE | This observation has 180 degrees target motion, and possible SRU violations at closest approach (depending on secondary chosen). | Please include a 20 minute quiescent period due to the target motion, and either design with no SRU violations or include proper quiescent periods for that as well. The designer should provide the quiescent period time to the SIP lead in time for the science forum so AACS can use in in their RBOT analysis.
S91000199 | ISS | 2015-273T07:50:00 | ISS_222DI_DIONE002_PIE | This and the observations immediately before and after have total target (Dione) motion of 122 degrees over 3h30m. | Any observation >3 hours in which the target body travels > 60 degrees must include 20 minute quiescent periods every 3 hours. The last 20 minutes of this observation is at an inertial attitude to satisfy this guideline.
S91000204 | CIRS | 2015-328T04:15:00 | CIRS_226SA_LIMBINT001_PIE | The target of this observation -- Saturn -- covers 80 degrees of sky during the course of this six-hour observation. The requirement is <60 degrees of motion in a 3 hour observation. | The observation must include an inertially fixed quiescent period of 20 minutes. The designer should provide the quiescent period time to the SIP lead in time for the science forum so AACS can use in in their RBOT analysis.
S91000205 | CIRS | 2015-327T20:00:00 | CIRS_226TE_TETHYS001_PIE | The target of this observation -- Tethys -- covers 150 degrees of sky during the course of this three-hour, thirty-minute observation. | The observation must include an inertially fixed quiescent period of 20 minutes. The designer should provide the quiescent period time to the SIP lead in time for the science forum so AACS can use in in their RBOT analysis.
S91000206 | MP SP | 2015-267T23:48:12 | Delay Canberra HEF maintenance | According to CIMS, the Canberra Complex is down from 267T20:32 - 268T02:32. The Canberra HEF is requested from 267T23:48 - 08:48. This is an OTM Prime Pass. | Request delay of Canberra HEF maintenance until after OTP pass is complete.
S91000207 | CDS ENGR SP | 2015-273T02:02:00 | ENGR_222NA_DUALPB271_CDS | This is a non-standard dual playback, with carryover on SSRs prior to high-value observation period as well as prior to the dual playback pass. During DSN negotiations, ensure that SSR-A is emptied before the pointers are reset. This item cannot be closed until the DSN negotiations are complete for both downlink passes, or the dual playback is deleted. | Resolve during DSN negotiations.
S91000208 | MP SP | 2015-280T23:01:00 | Delay Canberra BWG Maintenance | According to CIMS, the Canberra Complex is down from 280T19:31 - 281T01:31. The Canberra BWG station is requested from 280T23:01 - 08:01. | Request delay of Canberra BWG maintenance until downlink is complete.
S91000209 | CIRS INMS RADAR SP | 2015-271T20:37:12 | INMS_222TI_TITAN113001_PRIME | T113: INMS inbound and RADAR C/A observations both have CIRS heating. At PSG for T113 CAPS reallocation, CIRS has agreed to accept a heating consumable up to 14.4K above T0. | Ensure the INMS and RADAR T113 observations together do not heat CIRS beyond 14.4K above T0, or CIRS to accept a new heating consumable value.
S91000297 | CIRS INMS SP VIMS | 2015-301T13:30:00 | INMS_224EN_ENCEL21001_PIE | INMS_224EN_ENCEL21001_PIE has ~ 12.9 K of CIRS heating, and also a high amount of VIMS heating. | Get preliminary approval from CIRS and VIMS, write and approve waiver during SIP process.